## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-SWEN-261-05-3C-The_Juicebox_Squad
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket.
As a Helper I want to remove needs from my Fund Basket so that I may hold control over what I purchase. | Given that A user has items in their Fund Basket when i press remove from cart then i expect the item is removed. | Pass
As a Helper I want to be able to add items in the Fund Basket so that I can check them out. | Given that a user sees a need when they press add to cart then i expect that the item is added to the Fund Basket. | Fail | SMN; 10/26/23; Item Enters as Null
As a User I want to Log in so that i can access the site. | Given a User creates an account when i log in then my previous account information is saved | Pass | SMN; 10/26/23; Working
| Given that a User creates an account when a new user tries to use the same username then it asks the user to enter a different username. | Pass
As a User i want to be able to log into my username. | Given the initialization of the website When I enter my username Then all of my information is made available | Pass
As a Admin I want to add to the cupboard so that the orphan needs are met | Given that the Admin is logged in when the Admin adds to the cupboard then the cupboard should be updated. | Pass
As an Admin I want to edit the position and data of the needs in the cupboard so that the cupboard is more organized and regulated to the product owner’s wishes. | Given that Admin is logged in when they edit the cupboard then the cupboard should be updated with the changes | Pass
As an Admin I want to be able to add/remove/edit inventory. | Given that their are items in the inventory when an admin changes the list then the Inventory is updated. | Pass
As an Admin I want to remove needs from the Cupboard so that the helper can be given the proper selection of donatable needs. | Given that the cupboard has at least one need when I press on a remove button then I expect the need to be removed from the cupboard. | Pass | SMN; 10/26/23; Working
As a Helper I want to be able to see my shopping cart so that i know what I'm buying | Given a Helper has been added to the shopping cart when I press on the shopping cart then I can view the items in the Fund Basket. | Fail | JL; 10/26/23; TestConstructorNotNull failed
As a Helper I want to select orphan needs to support so that I can feel good about myself. | Given a Helper has selected needs to support When they're looking at a list of needs Then add the specific support values to the Helper's Fund Basket. | Fail | CP; 10/26/23; not implemented
As a Helper I want to be able to pay for my items so I can checkout. | Given a Helper moves to checkout their Funds Basket When they've selected specific needs to support Then allow them to complete the transaction. | Fail | JD; 10/26/23; not implemented